## Slide 1: Evaluation and Learning PGRI Indonesia
<number>

## Slide 2
<number>
Notes: <number>

## Slide 3
1.9 million members in village, school and educational units
68,139 Sub Branch Boards (7 leaders and average members per sub-board 27.88)
4,288 Branch Boards (3 elected out of 15 leaders and average members per Branch 443)
33 Provincial Boards (5 elected out of 19 leaders and average membership per province 57,575)
412 District Boards (4 elected out of 17 leaders and average members per district 4,611)
National Board (7 elected out of 25 leaders and 1.9 million members)

## Slide 5: Background
After the fall of Suharto in 1998, PGRI resolved to establish itself as an independent professional teachers’ trade union organisation.
On the PGRI’s request, AEU, JTU, Lararforbundet, NEA and UEN formed an EI consortium and started to support the PGRI’s effort from 2000.
The partnership has run over 400 activities providing training to over 13,500 officials and ordinary members.
The programme was annually evaluated and planned and was expanded to more and more provinces for more than a decade.
There was a need to authenticate the reports and information obtained during the internal evaluations.
<number>

## Slide 6: External Evaluation
The EI and Consortium partners in consultation with the PGRI decided to undertake an independent external evaluation
Prof. Michele Ford of the Sydney University was nominated as the lead consultant for the evaluation.
The purpose of the evaluation was to
  Assess the results of the project in terms of organisational development and how sustainable the results are
  Identify any unintended effects and results
  Make recommendations for operational planning for future
<number>

## Slide 7: Evaluation Process
The evaluator was required to collect first hand information from 3 independently selected provinces through personal interviews at all levels.
Three target areas for evaluation were selected based on the PGRI recommendations to be the most effective, the medium and the least effective. .
After necessary assessment the evaluator submitted findings to all partners in a feed-back seminar.
<number>

## Slide 8: Response
Among the six recommendations, the PGRI did not accept one recommendation that suggested elimination of branch committees which are barrier to good communication between the grass-root and the districts
<number>

## Slide 9: Findings - recommendations
The report attributed many successes in the organisational development of the PGRI to the consortium project but questioned relevance, effectiveness and sustainability of the programme.
It was recommended to improve programme format, methodology, resource persons and materials for the activities
It was recommended that the PGRI leadership renew their commitment to change and build internal education and training capacity.
<number>

## Slide 10: Impact of the evaluation
The external evaluation facilitated better cooperation and mutual understanding between all the parties enabling immediate improvements in the programme design, resource persons and materials of the project.
Training of new resource persons and 17 activities under the revised design has been completed in a very short time.
<number>

## Slide 11: Lessons learnt
External evaluation is challenging and mutual understanding among the partners is vital
Evaluation should not be of the organisation but of the programme
All parties including the external evaluator should be involved from the beginning of the evaluation including in the design of the evaluation process
The evaluator should have good understanding of national context culture and language.
The evaluation findings should be shared widely among all partners and their constituencies to maximize the impact
<number>

## Slide 12: Lessons learnt
The external evaluations are helpful in developing new appropriate strategies
They are to be held periodically
I am of the view that such evaluation will be beneficial to all DC programmes.
<number>